## Request
SEDDMS Team Ref: | Date Received | Status | Actioned by | Date Issued | Expected Return | Calendar Invite | Date Testing | Date Upload | Area | Route | Requested By | Catchments | Issued to | Project | Purpose | Survey Contractor | NH Project Manager | Remarks
SEDDMS0007 | 2023-03-03 | Complete | DW | 2023-03-03 | - |  | 2023-03-09 | 2023-03-09 | Area 4 | A21 | Leah Westwood - DDC | SE04_A21_01 | Leah Westwood | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0008 | 2023-03-06 | Complete | DW | 2023-03-06 | - |  | 2023-03-06 | 2023-03-07 | Area 3 | A31 | Leah Westwood - DDC | A03_A31_23, A03_A31_24 | Leah Westwood | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan | A03_A31_23 - Unlocked for testing and uploaded 06/03/2023 A03_A31_24 Unlocked for testing and uploaded 07/03/2023
SEDDMS0009 | 2023-03-06 | Complete | DW | 2023-03-06 | - |  | 2023-03-08 | 2023-03-09 | Area 3 | A31 | Leah Westwood - DDC | Area3_A03_A31_22 | Leah Westwood | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0010 | 2023-03-06 | Complete | DW | 2023-03-06 | - |  | 2023-03-08 | 2023-03-09 | Area 3 | A31 | Leah Westwood - DDC | Area3_A03_A31_21a | Leah Westwood | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0011 | 2023-03-06 | Complete | DW | 2023-03-06 | - |  | 2023-03-08 | 2023-03-09 | Area 3 | A31 | Leah Westwood - DDC | Area3_A03_A31_20a | Leah Westwood | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0012 | 2023-03-06 | Complete | DW | 2023-03-06 | - |  | 2023-03-08 | 2023-03-09 | Area 3 | A31 | Leah Westwood - DDC | Area3_A03_A31_19c | Leah Westwood | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0013 | 2023-03-08 | Issued | DW | 2023-03-08 | 2023-06-22 |  |  |  | Area 4 | A2 | Clive Hemmings - R&W | A04_A2_21 | Clive Hemmings | A2 Whitfield FH356 | Post project survey | Conway | Nicola Carley
SEDDMS0014 | 2023-03-09 | Complete | DW | 2023-03-09 | - |  | 2023-03-20 | 2023-03-20 | Area 4 | A21 | Leah Westwood - DDC | 041_2018_A21_001 | Leah Westwood | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0015 | 2023-03-09 | Complete | DW | 2023-03-09 | - |  | 2023-03-17 | 2023-03-20 | Area 4 | M23 | Leah Westwood - DDC | A04_M23_05.1 | Leah Westwood | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0016 | 2023-03-09 | Complete | DW | 2023-03-09 | - |  | 2023-03-31 | 2023-04-12 | Area 3 | M4 | Leah Westwood - DDC | area3_M4_29d | Leah Westwood | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0017 | 2023-03-09 | Complete | DW | 2023-03-09 | - |  | 2023-04-27 | 2023-04-28 | Area 3 | M3 | Leah Westwood - DDC | A03_M3_05 | Leah Westwood | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0018 | 2023-03-09 | Complete | DW | 2023-03-09 | - |  | 2023-04-13 | 2023-04-14 | Area 3 | M3 | Leah Westwood - DDC | A03_M3_02 | Leah Westwood | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0019 | 2023-03-09 | Complete | DW | 2023-03-09 | - |  | 2023-03-17 | 2023-04-19 | Area 3 | M3 | Leah Westwood - DDC | A03_M3_01 | Leah Westwood | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0020 | 2023-03-10 | Complete | DW | 2023-03-10 | - |  | 2023-04-27 | 2023-05-05 | Area 4 | A21 | Leah Westwood - DDC | SE04_A21_02 | Leah Westwood | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0021 | 2023-03-15 | Complete | DW | 2023-03-15 | - |  | 2023-03-17 | 2023-03-21 | Area 4 | A2 | Raahil Ali - DDC | A04_A2_03 | Raahil Ali | Drainage Inspections | Inspection/update | DDC | Phil Morgan
SEDDMS0022 | 2023-03-17 | Complete | DW | 2023-03-17 | 2023-06-16 |  | 2023-04-13 | 2023-05-25 | Area 4 | A27 | Clive Hemmings - R&W | A04_A27_81.2 | Clive Hemmings | A27 Polegate to Shepham Lane | Post project survey | FM Conway | Dave Hughes
SEDDMS0023 | 2023-03-17 | Complete | DW | 2023-03-17 | 2023-06-16 |  | 2023-04-13 | 2023-04-17 | Area 4 | A27 | Clive Hemmings - R&W | A04_A27_82.1 | Clive Hemmings | A27 Polegate to Shepham Lane | Post project survey | FM Conway | Dave Hughes
SEDDMS0024 | 2023-03-23 | Testing | DW | 2023-03-23 | 2023-04-14 |  | 2023-05-24 |  | Area 4 | A27 | Veljko Komad | A04_A27_25 | Marcus.mullaney marcus.mullaney@knightsbrown.co.uk | 601722, A27 Fontwell roundabout | Post project survey | Sweeptech Survey | Robert Mackenzie
SEDDMS0025 | 2023-03-24 | Complete | DW | 2023-03-24 | 2023-05-05 |  | - | 2023-03-28 | Area 3 | M27 | Saqib Khan | Area3_M27_11c | Saqib Khan | M27 Jn 10 Improvement PIN NH611901 | Pre project survey | Lanes | Spyros Papanas | Cancelled - No update.
SEDDMS0026 | 2023-03-29 | Issued | DW | 2023-03-29 | 2023-04-21 |  |  |  | Area 4 | A2070 | Veljko Komad | A04_A2070_02 | Veljko Komad | A2070 Finberry Park PIN 565154 | Post project survey | FM Conway | Adela Montes Lopez | Brendan O’Sullivan, email: brendan.osullivan@fmconway.co.uk
SEDDMS0027 | 2023-04-05 | Complete | DW | 2023-04-05 | 2023-05-26 |  | 2023-05-19 | 2023-05-22 | Area 4 | A23 | Raahil Ali - DDC | A04_A23_12.1 | Raahil Ali | A23 Ponds 1&2 | Pre project survey | DDC | AbdelMauz Bakri
SEDDMS0028 | 2023-04-14 | Complete | DW | 2023-04-14 | 2023-05-26 |  | - | 2023-04-25 | Area 4 | M23 | Raahil Ali - DDC | A04_M23_05.1 | Raahil Ali | M23 Crawley (Culvert) Pin 611776 | CS551 Survey | DDC | Michelle Frain | Cancelled, No update to be issued for another project first.
SEDDMS0029 | 2023-04-20 | Complete | DW | 2023-04-20 | 2023-05-18 |  | 2023-05-02 | 2023-05-03 | Area 4 | A27 | Simon Lewis - DDC | SE04_A27_09 | Simon Lewis | Drainage Inspections | Inspection/update | DDC | Phil Morgan
SEDDMS0030 | 2023-04-20 | Complete | DW | 2023-04-20 | 2023-05-18 |  | 2023-05-02 | 2023-05-03 | Area 4 | A27 | Simon Lewis - DDC | SE04_A27_10 | Simon Lewis | Drainage Inspections | Inspection/update | DDC | Phil Morgan
SEDDMS0031 | 2023-04-20 | Complete | DW | 2023-04-20 | 2023-05-18 |  | 2023-05-02 | 2023-05-03 | Area 4 | A27 | Simon Lewis - DDC | SE04_A27_11 | Simon Lewis | Drainage Inspections | Inspection/update | DDC | Phil Morgan
SEDDMS0032 | 2023-04-20 | Complete | DW | 2023-04-24 | 2023-05-11 |  | 2023-04-26 | 2023-04-26 | Area 4 | A27 | Simon Lewis - DDC | SE04_A27_12 | Simon Lewis | Drainage Inspections | Inspection/update | DDC | Phil Morgan
SEDDMS0033 | 2023-04-20 | Complete | DW | 2023-04-20 | 2023-05-18 |  | 2023-05-02 | 2023-05-03 | Area 4 | A27 | Simon Lewis - DDC | SE04_A27_13 | Simon Lewis | Drainage Inspections | Inspection/update | DDC | Phil Morgan
SEDDMS0034 | 2023-04-20 | Complete | DW | 2023-04-20 | 2023-05-18 |  | 2023-05-02 | 2023-05-03 | Area 4 | A27 | Simon Lewis - DDC | SE04_A27_14 | Simon Lewis | Drainage Inspections | Inspection/update | DDC | Phil Morgan
SEDDMS0035 | 2023-04-20 | Complete | DW | 2023-05-19 | - |  | 2023-05-23 | 2023-05-24 | Area 4 | A27 | Simon Lewis - DDC | A04_A27_20.1 | Simon Lewis | Drainage Inspections | Inspection/update | DDC | Phil Morgan
SEDDMS0036 | 2023-04-20 | Complete | DW | 2023-04-20 | 2023-05-18 |  | 2023-05-04 | 2023-05-09 | Area 4 | A27 | Simon Lewis - DDC | A04_A27_24 | Simon Lewis | Drainage Inspections | Inspection/update | DDC | Phil Morgan
SEDDMS0037 | 2023-04-20 | Reserve | DW | [5 empty] | Area 4 | A27 | Simon Lewis - DDC | A04_A27_25 |  | Drainage Inspections | Inspection/update | DDC | Phil Morgan
SEDDMS0038 | 2023-04-20 | Complete | DW | 2023-04-20 | 2023-05-18 |  | 2023-05-04 | 2023-05-09 | Area 4 | A27 | Simon Lewis - DDC | A04_A27_26 | Simon Lewis | Drainage Inspections | Inspection/update | DDC | Phil Morgan
SEDDMS0039 | 2023-04-20 | Complete | DW | 2023-04-20 | 2023-05-18 |  | 2023-05-04 | 2023-05-09 | Area 4 | A27 | Simon Lewis - DDC | A04_A27_30 | Simon Lewis | Drainage Inspections | Inspection/update | DDC | Phil Morgan
SEDDMS0040 | 2023-04-20 | Complete | DW | 2023-04-20 | 2023-05-18 |  | 2023-05-04 | 2023-05-09 | Area 4 | A27 | Simon Lewis - DDC | A04_A27_44 | Simon Lewis | Drainage Inspections | Inspection/update | DDC | Phil Morgan
SEDDMS0041 | 2023-04-20 | Complete | DW | 2023-04-20 | 2023-05-18 |  | 2023-05-04 | 2023-05-09 | Area 4 | A27 | Simon Lewis - DDC | A04_A27_48.1 | Simon Lewis | Drainage Inspections | Inspection/update | DDC | Phil Morgan
SEDDMS0042 | 2023-04-20 | Complete | DW | 2023-04-20 | 2023-05-18 |  | 2023-05-04 | 2023-05-09 | Area 4 | A27 | Simon Lewis - DDC | A04_A27_49 | Simon Lewis | Drainage Inspections | Inspection/update | DDC | Phil Morgan
SEDDMS0043 | 2023-04-20 | Complete | DW | 2023-04-20 | 2023-05-18 |  | 2023-05-12 | 2023-05-15 | Area 4 | A27 | Simon Lewis - DDC | A04_A27_50 | Simon Lewis | Drainage Inspections | Inspection/update | DDC | Phil Morgan
SEDDMS0044 | 2023-04-20 | Complete | DW | 2023-04-20 | 2023-05-18 |  | 2023-05-12 | 2023-05-15 | Area 4 | A27 | Simon Lewis - DDC | A04_A27_53 | Simon Lewis | Drainage Inspections | Inspection/update | DDC | Phil Morgan
SEDDMS0045 | 2023-04-20 | Complete | DW | 2023-04-20 | 2023-05-18 |  | 2023-05-12 | 2023-05-15 | Area 4 | A27 | Simon Lewis - DDC | A04_A27_54 | Simon Lewis | Drainage Inspections | Inspection/update | DDC | Phil Morgan
SEDDMS0046 | 2023-04-20 | Complete | DW | 2023-04-20 | 2023-05-18 |  | 2023-05-12 | 2023-05-15 | Area 4 | A27 | Simon Lewis - DDC | A04_A27_55 | Simon Lewis | Drainage Inspections | Inspection/update | DDC | Phil Morgan
SEDDMS0047 | 2023-04-20 | Complete | DW | 2023-04-20 | 2023-05-18 |  | 2023-05-12 | 2023-05-15 | Area 4 | A27 | Simon Lewis - DDC | A04_A27_56.1 | Simon Lewis | Drainage Inspections | Inspection/update | DDC | Phil Morgan
SEDDMS0048 | 2023-04-20 | Reserve | DW | [5 empty] | Area 4 | A27 | Simon Lewis - DDC | A04_A27_64 |  | Drainage Inspections | Inspection/update | DDC | Phil Morgan
SEDDMS0049 | 2023-04-21 | Complete | DW | 2023-04-21 | - |  | 2023-04-27 | 2023-04-28 | Area 4 | A21 | Alen Babu - DDC | SE04_A21_04 | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0050 | 2023-04-21 | Complete | DW | 2023-04-21 | - |  | 2023-04-27 | 2023-04-28 | Area 4 | A21 | Alen Babu - DDC | SE04_A21_05 | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0051 | 2023-04-21 | Complete | DW | 2023-04-21 | - |  | 2023-04-27 | 2023-04-28 | Area 4 | A21 | Alen Babu - DDC | SE04_A21_06 | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0052 | 2023-04-21 | Complete | DW | 2023-04-21 | - |  | 2023-04-27 | 2023-04-28 | Area 4 | A21 | Alen Babu - DDC | SE04_A21_07 | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0053 | 2023-04-21 | Complete | DW | 2023-04-21 | - |  | 2023-05-04 | 2023-05-05 | Area 4 | A21 | Alen Babu - DDC | SE04_A21_08 | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0054 | 2023-04-21 | Complete | DW | 2023-04-21 | - |  | 2023-05-04 | 2023-05-05 | Area 4 | A21 | Alen Babu - DDC | SE04_A21_09 | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0055 | 2023-04-25 | Complete | DW | 2023-04-25 | 2023-05-19 |  | - | 2023-05-09 | Area 4 | M23 | Clive Hemmings - R&W | A04_M23_05.1 | Clive Hemmings | M23 Culvert Cleanse | Post project survey | FM Conway | Wayne Moore
SEDDMS0056 | 2023-04-25 | Complete | DW | 2023-04-25 | - |  | 2023-04-28 | 2023-04-28 | Area 3 | A31 | Alen Babu - DDC | A03_A31_28 | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0057 | 2023-04-25 | Complete | DW | 2023-04-25 | - |  | 2023-04-28 | 2023-04-28 | Area 3 | A31 | Alen Babu - DDC | A03_A31_29 | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0058 | 2023-04-25 | Complete | DW | 2023-04-25 | - |  | 2023-04-28 | 2023-04-28 | Area 3 | A31 | Alen Babu - DDC | A03_A31_30 | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0059 | 2023-04-25 | Complete | DW | 2023-04-25 | - |  | 2023-04-28 | 2023-04-28 | Area 3 | A31 | Alen Babu - DDC | A03_A31_31 | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0060 | 2023-04-25 | Complete | DW | 2023-04-25 | - |  | 2023-04-27 | 2023-04-28 | Area 3 | M3 | Alen Babu - DDC | A03_M3_02 | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0061 | 2023-04-26 | Issued | DW | 2023-04-27 | 2023-06-02 |  |  |  | Area 4 | A27 | Peter Dodds - SDS | SE04_A27_12 | Peter Dodds | Local Authority - Third Party works | Post project survey | SDS | -
SEDDMS0062 | 2023-04-27 | Complete | DW | 2023-04-27 | - |  | 2023-05-11 | 2023-05-15 | Area 3 | M3 | Alen Babu - DDC | A03_M3_03 | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0063 | 2023-04-27 | Complete | DW | 2023-04-27 | - |  | 2023-05-11 | 2023-05-18 | Area 3 | M3 | Alen Babu - DDC | A03_M3_04 | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0064 | 2023-05-05 | Complete | DW | 2023-05-05 | 2023-06-14 |  | 2023-05-24 | 2023-05-24 | Area 3 | M27 | Jack Stapley - FMC | Area3_M27_11c | Jack Stapley | M27 J10-29 West Downs Close | Pre project survey | FM Conway | Anup Shrestha
SEDDMS0065 | 2023-05-09 | Issued | DW | 2023-05-09 |  |  |  |  | Area 4 | M23 | Raahil Ali - DDC | A04_M23_05.1 | Raahil Ali | M23 Crawley (Culvert) Pin 611776 | CS551 Survey | DDC | Michelle Frain
SEDDMS0066 | 2023-05-09 | Complete | DW | 2023-05-09 | - |  | 2023-05-18 | 2023-05-22 | Area 3 | A31 | Alen Babu - DDC | A03_A31_24 | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0067 | 2023-05-09 | Complete | DW | 2023-05-09 | - |  | 2023-05-18 | 2023-05-24 | Area 3 | A31 | Alen Babu - DDC | A03_A31_25 | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0068 | 2023-05-09 | Complete | DW | 2023-05-09 | - |  | 2023-05-18 | 2023-06-05 | Area 3 | A31 | Alen Babu - DDC | A03_A31_26 | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0069 | 2023-05-09 | Complete | DW | 2023-05-09 | - |  | 2023-05-18 | 2023-06-05 | Area 3 | A31 | Alen Babu - DDC | A03_A31_27 | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0070 | 2023-05-09 | Complete | DW | 2023-05-09 | - |  | 2023-05-11 | 2023-05-12 | Area 4 | A21 | Alen Babu - DDC | SE04_A21_13 | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0071 | 2023-05-09 | Complete | DW | 2023-05-09 | - |  | 2023-05-11 | 2023-05-12 | Area 4 | A21 | Alen Babu - DDC | SE04_A21_14 | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0072 | 2023-05-09 | Complete | DW | 2023-05-09 | - |  | 2023-05-11 | 2023-05-12 | Area 4 | A21 | Alen Babu - DDC | SE04_A21_15 | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0073 | 2023-05-09 | Complete | DW | 2023-05-09 | - |  | 2023-05-11 | 2023-05-12 | Area 4 | A21 | Alen Babu - DDC | SE04_A21_16 | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0074 | 2023-05-09 | Complete | DW | 2023-05-09 | - |  | 2023-05-11 | 2023-05-12 | Area 4 | A21 | Alen Babu - DDC | SE04_A21_18 | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0075 | 2023-05-09 | Complete | DW | 2023-05-09 | - |  | 2023-05-11 | 2023-05-12 | Area 4 | A21 | Alen Babu - DDC | SE04_A21_19 | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0076 | 2023-05-10 | Testing | DW | 2023-05-10 | 2023-05-26 |  | 2023-05-26 |  | Area 4 | M23 | Raahil Ali - DDC | A04_M23_05.1 | Raahil Ali | M23 Crawley (Culvert) Pin 611776 | CS551 Survey | DDC | Michelle Frain
SEDDMS0077 | 2023-05-11 | Testing | DW | 2023-05-11 | 2023-05-31 |  | 2023-05-25 |  | Area 4 | A27 | Chris Harding - Volker's | A04_A27_68 | Chris Harding | A27 East of Lewes | Post project survey | FM Conway | Thomas Beasley
SEDDMS0078 | 2023-05-11 | Testing | DW | 2023-05-11 | 2023-05-31 |  | 2023-05-25 |  | Area 4 | A27 | Chris Harding - Volker's | A04_A27_69 | Chris Harding | A27 East of Lewes | Post project survey | FM Conway | Thomas Beasley
SEDDMS0079 | 2023-05-11 | Complete | DW | 2023-05-11 | - |  | 2023-05-18 | 2023-05-22 | Area 4 | A21 | Alen Babu - DDC | SE04_A21_22 | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0080 | 2023-05-11 | Complete | DW | 2023-05-11 | - |  | 2023-05-18 | 2023-05-22 | Area 4 | A21 | Alen Babu - DDC | SE04_A21_23 | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0081 | 2023-05-11 | Complete | DW | 2023-05-11 | - |  | 2023-05-18 | 2023-05-22 | Area 4 | A21 | Alen Babu - DDC | SE04_A21_25 | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0082 | 2023-05-11 | Complete | DW | 2023-05-11 | - |  | 2023-05-18 | 2023-05-22 | Area 4 | A21 | Alen Babu - DDC | SE04_A21_30 | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0083 | 2023-05-11 | Complete | DW | 2023-05-11 | - |  | 2023-05-18 | 2023-05-22 | Area 4 | A21 | Alen Babu - DDC | SE04_A21_31 | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0084 | 2023-05-11 | Complete | DW | 2023-05-11 | 2023-06-15 |  | 2023-05-26 | 2023-05-26 | Area 3 | M27 | Jack Stapley - FMC | Area3_M27_07e | Jack Stapley | M27 Junction 5 Exit & Entry Slips | Pre project survey | FM Conway | Anup Shrestha
SEDDMS0085 | 2023-05-18 | Complete | DW | 2023-05-18 | - |  | 2023-05-19 | 2023-05-22 | Area 3 | A308 | Alen Babu - DDC | A03_A308M_01 | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0086 | 2023-05-18 | Complete | DW | 2023-05-18 | - |  | 2023-05-19 | 2023-05-22 | Area 3 | M4 | Alen Babu - DDC | M4_Catchment_10_3025 | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0087 | 2023-05-18 | Issued | DW | 2023-05-19 | 2023-08-18 |  |  |  | Area 3 | A34 | Raahil Ali - DDC | Area3_A34_03 | Raahil Ali | 613116 - VRS PDS Surveys | CS551 Survey | DDC | Dan Cooling
SEDDMS0088 | 2023-05-18 | Issued | DW | 2023-05-19 | 2023-08-18 |  |  |  | Area 3 | A34 | Raahil Ali - DDC | Area3_A34_04 | Raahil Ali | 613116 - VRS PDS Surveys | CS551 Survey | DDC | Dan Cooling
SEDDMS0089 | 2023-05-18 | Issued | DW | 2023-05-19 | 2023-08-18 |  |  |  | Area 3 | A34 | Raahil Ali - DDC | Area3_A34_05 | Raahil Ali | 613116 - VRS PDS Surveys | CS551 Survey | DDC | Dan Cooling
SEDDMS0090 | 2023-05-18 | Issued | DW | 2023-05-19 | 2023-08-18 |  |  |  | Area 3 | A34 | Raahil Ali - DDC | Area3_A34_06b | Raahil Ali | 613116 - VRS PDS Surveys | CS551 Survey | DDC | Dan Cooling
SEDDMS0091 | 2023-05-18 | Issued | DW | 2023-05-19 | 2023-08-18 |  |  |  | Area 3 | A34 | Raahil Ali - DDC | Area3_A34_07 | Raahil Ali | 613116 - VRS PDS Surveys | CS551 Survey | DDC | Dan Cooling
SEDDMS0092 | 2023-05-18 | Issued | DW | 2023-05-19 | 2023-08-18 |  |  |  | Area 3 | A34 | Raahil Ali - DDC | Area3_A34_12a | Raahil Ali | 613116 - VRS PDS Surveys | CS551 Survey | DDC | Dan Cooling
SEDDMS0093 | 2023-05-18 | Issued | DW | 2023-05-19 | 2023-08-18 |  |  |  | Area 3 | A34 | Raahil Ali - DDC | Area3_A34_22c | Raahil Ali | 613116 - VRS PDS Surveys | CS551 Survey | DDC | Dan Cooling
SEDDMS0094 | 2023-05-18 | Issued | DW | 2023-05-19 | 2023-08-18 |  |  |  | Area 3 | A34 | Raahil Ali - DDC | Area3_A34_25a | Raahil Ali | 613116 - VRS PDS Surveys | CS551 Survey | DDC | Dan Cooling
SEDDMS0095 | 2023-05-18 | Issued | DW | 2023-05-19 | 2023-08-18 |  |  |  | Area 3 | A34 | Raahil Ali - DDC | Area3_A34_26a | Raahil Ali | 613116 - VRS PDS Surveys | CS551 Survey | DDC | Dan Cooling
SEDDMS0096 | 2023-05-18 | Issued | DW | 2023-05-19 | 2023-08-18 |  |  |  | Area 3 | A34 | Raahil Ali - DDC | Area3_A34_28c | Raahil Ali | 613116 - VRS PDS Surveys | CS551 Survey | DDC | Dan Cooling
SEDDMS0097 | 2023-05-18 | Issued | DW | 2023-05-19 | 2023-08-18 |  |  |  | Area 3 | A34 | Raahil Ali - DDC | Area3_A34_29a | Raahil Ali | 613116 - VRS PDS Surveys | CS551 Survey | DDC | Dan Cooling
SEDDMS0098 | 2023-05-18 | Issued | DW | 2023-05-19 | 2023-08-18 |  |  |  | Area 3 | A34 | Raahil Ali - DDC | Area3_A34_30 | Raahil Ali | 613116 - VRS PDS Surveys | CS551 Survey | DDC | Dan Cooling
SEDDMS0099 | 2023-05-18 | Issued | DW | 2023-05-19 | 2023-08-18 |  |  |  | Area 3 | A34 | Raahil Ali - DDC | Area3_A34_31 | Raahil Ali | 613116 - VRS PDS Surveys | CS551 Survey | DDC | Dan Cooling
SEDDMS0100 | 2023-05-18 | Issued | DW | 2023-05-19 | 2023-08-18 |  |  |  | Area 3 | A34 | Raahil Ali - DDC | Area3_A34_40a | Raahil Ali | 613116 - VRS PDS Surveys | CS551 Survey | DDC | Dan Cooling
SEDDMS0101 | 2023-05-18 | Issued | DW | 2023-05-19 | 2023-08-18 |  |  |  | Area 3 | A34 | Raahil Ali - DDC | Area3_A34_41 | Raahil Ali | 613116 - VRS PDS Surveys | CS551 Survey | DDC | Dan Cooling
SEDDMS0102 | 2023-05-18 | Issued | DW | 2023-05-19 | 2023-08-18 |  |  |  | Area 3 | M3 | Raahil Ali - DDC | Area3_M3_09b | Raahil Ali | 613116 - VRS PDS Surveys | CS551 Survey | DDC | Dan Cooling
SEDDMS0103 | 2023-05-18 | Issued | DW | 2023-05-19 | 2023-08-18 |  |  |  | Area 3 | M3 | Raahil Ali - DDC | Area3_M3_12b | Raahil Ali | 613116 - VRS PDS Surveys | CS551 Survey | DDC | Dan Cooling
SEDDMS0104 | 2023-05-18 | Issued | DW | 2023-05-19 | 2023-08-18 |  |  |  | Area 3 | M3 | Raahil Ali - DDC | Area3_M3_13c | Raahil Ali | 613116 - VRS PDS Surveys | CS551 Survey | DDC | Dan Cooling
SEDDMS0105 | 2023-05-18 | Issued | DW | 2023-05-19 | 2023-08-18 |  |  |  | Area 3 | M4 | Raahil Ali - DDC | Area3_M4_26 | Raahil Ali | 613116 - VRS PDS Surveys | CS551 Survey | DDC | Dan Cooling
SEDDMS0106 | 2023-05-18 | Issued | DW | 2023-05-19 | 2023-08-18 |  |  |  | Area 3 | M4 | Raahil Ali - DDC | Area3_M4_27 | Raahil Ali | 613116 - VRS PDS Surveys | CS551 Survey | DDC | Dan Cooling
SEDDMS0107 | 2023-05-18 | Issued | DW | 2023-05-19 | 2023-08-18 |  |  |  | Area 3 | A3 | Raahil Ali - DDC | SE03_A3_08 | Raahil Ali | 613116 - VRS PDS Surveys | CS551 Survey | DDC | Dan Cooling
SEDDMS0108 | 2023-05-18 | Issued | DW | 2023-05-19 | 2023-08-18 |  |  |  | Area 3 | A3 | Raahil Ali - DDC | SE03_A3_21 | Raahil Ali | 613116 - VRS PDS Surveys | CS551 Survey | DDC | Dan Cooling
SEDDMS0109 | 2023-05-18 | Issued | DW | 2023-05-19 | 2023-08-18 |  |  |  | Area 3 | A3 | Raahil Ali - DDC | SE03_A3_22 | Raahil Ali | 613116 - VRS PDS Surveys | CS551 Survey | DDC | Dan Cooling
SEDDMS0110 | 2023-05-23 | Complete | DW | 2023-05-23 | - |  | 2023-05-24 | 2023-05-26 | Area 4 | M23 | Alen Babu - DDC | 04_4400 M23 SMP | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0111 | 2023-05-23 | Importing | DW | 2023-05-23 | - |  | 2023-05-24 | 2023-05-26 | Area 4 | M23 | Alen Babu - DDC | 04_4401 M23 SMP | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0112 | 2023-05-23 | Importing | DW | 2023-05-23 | - |  | 2023-05-24 | 2023-05-26 | Area 4 | M23 | Alen Babu - DDC | 04_4402 M23 SMP | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0113 | 2023-05-23 | Issued | DW | 2023-05-23 | - |  |  |  | Area 4 | M23 | Alen Babu - DDC | 04_4403 M23 SMP | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0114 | 2023-05-24 | Importing | DW | 2023-05-24 | - |  | 2023-05-24 | 2023-05-26 | Area 4 | M23 | Alen Babu - DDC | 041_2018_M23_002 | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0115 | 2023-05-24 | Importing | DW | 2023-05-24 | - |  | 2023-05-24 | 2023-05-26 | Area 4 | M23 | Alen Babu - DDC | 041_2018_M23_003.1 | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0116 | 2023-05-24 | uploaded | DW | 2023-05-24 | - |  | 2023-05-26 | 2023-06-05 | Area 4 | M23 | Alen Babu - DDC | A04_M23_03.1 | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0117 | 2023-05-24 | uploaded | DW | 2023-05-24 | 2023-06-21 |  |  | 2023-06-06 | Area 4 | A2 | Alexis Emm - FMC | A04_A2_02 | Alexis Emm | A2 Bean to Ebbsfleet Major project | Post project survey | FMC
SEDDMS0118 | 2023-05-24 | Importing | DW | 2023-05-24 | 2023-06-21 |  |  | 2023-06-06 | Area 4 | A2 | Alexis Emm - FMC | A04_A2_03 | Alexis Emm | A2 Bean to Ebbsfleet Major project | Post project survey | FMC
SEDDMS0119 | 2023-05-25 | Complete | DW | 2023-05-25 | - |  | 2023-05-26 | 2023-05-26 | Area 3 | M4 | Alen Babu - DDC | A03_M4_10 | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0120 | 2023-05-25 | Issued | DW | 2023-05-26 | 2023-08-01 |  |  |  | Area 3 | A31 | Jack Stapley - FMC | A03_A31_07 | Jack Stapley | A31 Gravel Lane, Ringwood | Post project survey | FMC | Anup Shrestha
SEDDMS0121 | 2023-05-25 | Reserve | DW |  | 2023-08-01 |  |  |  | Area 3 | A31 | Jack Stapley - FMC | A03_A31_08 |  | A31 Gravel Lane, Ringwood | Post project survey | FMC | Anup Shrestha
SEDDMS0122 | 2023-05-25 | Issued | DW | 2023-05-26 | - |  |  |  | Area 3 | A31 | Alen Babu - DDC | A03_A31_18 | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0123 | 2023-05-25 | Issued | DW | 2023-05-26 | - |  |  |  | Area 3 | A31 | Alen Babu - DDC | A03_A31_19 | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0124 | 2023-05-25 | Issued | DW | 2023-05-26 | - |  |  |  | Area 3 | A31 | Alen Babu - DDC | A03_A31_20 | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0125 | 2023-05-25 | Testing | DW | 2023-05-26 | - |  | 2023-06-01 |  | Area 3 | A31 | Alen Babu - DDC | A03_A31_21 | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0126 | 2023-05-25 | Testing | DW | 2023-05-26 | - |  | 2023-06-01 |  | Area 3 | A31 | Alen Babu - DDC | A03_A31_22 | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0127 | 2023-05-25 | Testing | DW | 2023-05-26 | - |  | 2023-06-01 |  | Area 3 | A31 | Alen Babu - DDC | A03_A31_23 | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0128 | 2023-05-26 | Complete | DW | 2023-05-26 | 2023-06-23 |  | 2023-06-01 | 2023-06-01 | Area 4 | A2 | Simon Lewis - DDC | A04_A2_07.2 | Simon Lewis | Drainage Inspections | Inspection/update | DDC | Phil Morgan
SEDDMS0129 | 2023-05-26 | Complete | DW | 2023-05-26 | 2023-06-23 |  | 2023-06-01 | 2023-06-01 | Area 4 | A2 | Simon Lewis - DDC | A04_A2_10 | Simon Lewis | Drainage Inspections | Inspection/update | DDC | Phil Morgan
SEDDMS0130 | 2023-05-26 | Complete | DW | 2023-05-26 | 2023-06-23 |  | 2023-06-01 | 2023-06-01 | Area 4 | A2 | Simon Lewis - DDC | A04_A2_11 | Simon Lewis | Drainage Inspections | Inspection/update | DDC | Phil Morgan
SEDDMS0131 | 2023-05-26 | Complete | DW | 2023-05-26 | 2023-06-23 |  | 2023-06-01 | 2023-06-01 | Area 4 | A2 | Simon Lewis - DDC | A04_A2_12 | Simon Lewis | Drainage Inspections | Inspection/update | DDC | Phil Morgan
SEDDMS0132 | 2023-05-26 | Complete | DW | 2023-05-26 | 2023-06-23 |  | 2023-06-01 | 2023-06-01 | Area 4 | A2 | Simon Lewis - DDC | A04_A2_13 | Simon Lewis | Drainage Inspections | Inspection/update | DDC | Phil Morgan
SEDDMS0133 | 2023-05-26 | Complete | DW | 2023-05-26 | 2023-06-23 |  | 2023-06-01 | 2023-06-01 | Area 4 | A2 | Simon Lewis - DDC | A04_A2_15 | Simon Lewis | Drainage Inspections | Inspection/update | DDC | Phil Morgan
SEDDMS0134 | 2023-05-26 | Complete | DW | 2023-05-26 | 2023-06-23 |  | 2023-06-01 | 2023-06-01 | Area 4 | A2 | Simon Lewis - DDC | A04_A2_17 | Simon Lewis | Drainage Inspections | Inspection/update | DDC | Phil Morgan
SEDDMS0135 | 2023-05-26 | Reserve | DW | [5 empty] | Area 4 | A2 | Simon Lewis - DDC | A04_A2_03 |  | Drainage Inspections | Inspection/update | DDC | Phil Morgan
SEDDMS0136 | 2023-05-31 | Issued | DW | 2023-06-01 | 2023-08-31 |  |  |  | Area 3 | A34 | Joanna Slicner | A03_A34_43 | Joanna Slicner | A34 Weston on the Green drainage | Post project survey | Crown+ | Kathryn Crow
SEDDMS0137 | 2023-06-01 | Issued | DW | 2023-06-01 | 2023-09-01 |  |  |  | Area 3 | M4 | Mark Wallace - BBVJV | A03_M4_14 | Mark Wallace | M4 Smart Jct 3 -12 | Data Cleanse | NRC | Steve Foxely
SEDDMS0138 | 2023-06-01 | Issued | DW | 2023-06-01 | 2023-09-01 |  |  |  | Area 3 | M4 | Mark Wallace - BBVJV | A03_M4_15 | Mark Wallace | M4 Smart Jct 3 -12 | Data Cleanse | NRC | Steve Foxely
SEDDMS0139 | 2023-06-01 | Issued | DW | 2023-06-01 | 2023-09-01 |  |  |  | Area 3 | M4 | Mark Wallace - BBVJV | A03_M4_16 | Mark Wallace | M4 Smart Jct 3 -12 | Data Cleanse | NRC | Steve Foxely
SEDDMS0140 | 2023-06-01 | Issued | DW | 2023-06-01 | 2023-09-01 |  |  |  | Area 3 | M4 | Mark Wallace - BBVJV | A03_M4_17 | Mark Wallace | M4 Smart Jct 3 -12 | Data Cleanse | NRC | Steve Foxely
SEDDMS0141 | 2023-06-01 | Issued | DW | 2023-06-01 | 2023-09-01 |  |  |  | Area 3 | M4 | Mark Wallace - BBVJV | A03_M4_18 | Mark Wallace | M4 Smart Jct 3 -12 | Data Cleanse | NRC | Steve Foxely
SEDDMS0142 | 2023-06-01 | Issued | DW | 2023-06-01 | 2023-09-01 |  |  |  | Area 3 | M4 | Mark Wallace - BBVJV | A03_M4_19 | Mark Wallace | M4 Smart Jct 3 -12 | Data Cleanse | NRC | Steve Foxely
SEDDMS0143 | 2023-06-01 | Issued | DW | 2023-06-01 | 2023-07-07 |  |  |  | Area 3 | M4 | Raahil Ali - DDC | A03_M4_10 | Raahil Ali | M4 J8-9 Geotech | CS551 Survey | DDC | Jennifer Downham
SEDDMS0144 | 2023-06-01 | Reserve | DW | [5 empty] | Area 3 | M4 | Mark Wallace - BBVJV | A03_M4_10 | Mark Wallace | M4 Smart Jct 3 -12 | Data Cleanse | NRC | Steve Foxely
SEDDMS0145 | 2023-06-01 | Reserve | DW | [5 empty] | Area 3 | M4 | Mark Wallace - BBVJV | A03_M4_11 | Mark Wallace | M4 Smart Jct 3 -12 | Data Cleanse | NRC | Steve Foxely
SEDDMS0146 | 2023-06-01 | Reserve | DW | [5 empty] | Area 3 | M4 | Mark Wallace - BBVJV | A03_M4_12 | Mark Wallace | M4 Smart Jct 3 -12 | Data Cleanse | NRC | Steve Foxely
SEDDMS0147 | 2023-06-01 | Reserve | DW | [5 empty] | Area 3 | M4 | Mark Wallace - BBVJV | A03_M4_13 | Mark Wallace | M4 Smart Jct 3 -12 | Data Cleanse | NRC | Steve Foxely
SEDDMS0148 | 2023-06-01 | Issued | DW | 2023-06-01 | 2023-07-07 |  |  |  | Area 4 | A23 | Raahil Ali - DDC | A04_A23_12.1 | Raahil Ali | A23 Pond 1 and 2 Scheme | Pre project survey | DDC | Alex Shrubshall
SEDDMS0149 | 2023-06-05 | Issued | DW | 2023-06-05 | - |  |  |  | Area 3 | A404(M) | Alen Babu - DDC | A03_A404M_01 | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0150 | 2023-06-05 | Issued | DW | 2023-06-05 | - |  |  |  | Area 3 | A404(M) | Alen Babu - DDC | A03_A404M_02 | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0151 | 2023-06-05 | Issued | DW | 2023-06-05 | - |  |  |  | Area 3 | A404(M) | Alen Babu - DDC | A03_A404M_03 | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0152 | 2023-06-05 | Issued | DW | 2023-06-05 | - |  |  |  | Area 3 | A308 | Alen Babu - DDC | A03_A308M_01 | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0153 | 2023-06-05 | Issued | DW | 2023-06-05 | - |  |  |  | Area 4 | M23 | Alen Babu - DDC | A04_M23_06 | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0154 | 2023-06-05 | Issued | DW | 2023-06-05 | - |  |  |  | Area 4 | M23 | Alen Babu - DDC | A04_M23_07 | Alen Babu | DDMS Data Cleanse | Data Cleanse | DDC | Phil Morgan
SEDDMS0155 | 2023-06-06 | Issued | DW | 2023-06-06 | 2023-08-18 |  |  |  | Area 3 | A34 | Raahil Ali - DDC | A03_A34_21 | Raahil Ali | 613116 - VRS PDS Surveys | CS551 Survey | DDC | Dan Cooling